## Ark1
			PLANING					DESIGN					DESIGN					BUILD					BUILD
			WEEK 1					WEEK 2					WEEK 3					WEEK 4					WEEK 5
			DAY 1	DAY 2	DAY 3	DAY 4	DAY 5		DAY 6	DAY 7	DAY 8	DAY 9	DAY 10		DAY 11	DAY 12	DAY 13	DAY 14	DAY 15		DAY 16	DAY 17	DAY 18	DAY 19	DAY 20		DAY 21	DAY 22	DAY 23	DAY 24	DAY 25
PROJECT MANAGER			PROJECT MANAGEMENT, CUSTOMER CONTACT, PROPOSAL AND CONTRACT					PROJECT MANAGEMENT, CUSTOMER CONTACT, PROPOSAL AND CONTRACT					PROJECT MANAGEMENT, CUSTOMER CONTACT, PROPOSAL AND CONTRACT					PROJECT MANAGEMENT, CUSTOMER CONTACT, PROPOSAL AND CONTRACT					PROJECT MANAGEMENT, CUSTOMER CONTACT, PROPOSAL AND CONTRACT

PROJECT MANAGER / CONTENT DEVELOPER			PROJECT START / INITIAL MEETING

PROJECT MANAGER / CONTENT DEVELOPER / DESIGNER			IDENTIFIYNG GOALS / NEED ASSESSMENT / PROJECT PLANING

CONTENT DEVELOPER / DESIGNER				RESEARCH

PROJECT MANAGER / CONTENT DEVELOPER / DESIGNER					STRATIGIC PLANNING

CONTENT DEVELOPER					CONTENT PLANNING

DEVELOPER / CONTENT DEVELOPER					SITE OUTLINE		SITE STRUCTURE
PROJECT MANAGER / CONTENT DEVELOPER / DESIGNER / DEVELOPER					CLIENT MEETING / FEEDBACK

PHOTOGRAPHER					PHOTOGRAPH PRODUCTLINE AND LOCATION / PRODUCTION

DESIGNER					STYLE TILE / MOODBOARD				MOCKUP		WIREFRAMES

CONTENT DEVELOPER					TEXT CONTENT DEVELOPMENT

PROJECT MANAGER / CONTENT DEVELOPER / DESIGNER					CLIENT MEETING / FEEDBACK					CLIENT MEETING / FEEDBACK

CONTENT DEVELOPER					SEARCH ENGINE OPTIMAZATION(SEO)

CONTENT DEVELOPER / DESIGNER					UX / UI DESIGN +				TEST

DEVELOPER					CODING, SITE BUILDING AND CONTENT INTEGRATION

DEVELOPER / PROJECT MANAGER / DESIGNER / CONTENT DEVELOPER					CLIENT MEETING / FEEDBACK

DEVELOPER					CROSSPLATFORM BROWSER TESTING

DEVELOPER					VALIDATING

CONTENT DEVELOPER / DESIGNER / DEVELOPER					REFEINMENT

DEVELOPER / PROJECT MANAGER / DESIGNER / CONTENT DEVELOPER					LAUNCH